## Checklist
TRMNGR
powered by Inkable Clothing ¦ trmngr.com
Tour manager checklist
Mark Done with Y. Progress updates automatically.
Cream cells are inputs. White cells with formulas update automatically.
Item | Done | Notes
Pre-tour
Contracts collected, dates confirmed
Budget and cash float plan
Routing, hotels, vehicles, flights booked
Contacts, IDs, dietary needs collected
Stage plot, input list, riders updated
Shared calendar and crew access set
Merch ordered; prices and count system
Insurance and gear inventory with serials
Advance (each show)
Contacts and schedule confirmed
Production, power, backline confirmed
Parking and load-in details
Hospitality / buyout confirmed
Merch fees and seller confirmed
Settlement time, method, person
Guest list allowance and deadline
Day of show
Day sheet out the night before
Arrive at access; meet venue contact
Load in, line check, soundcheck on time
Guest list to box office by deadline
Merch count in
Doors and set times called
Settle box office, expenses, deal, merch
Count cash with a witness; log it
Load out; room check; bus call
After the tour
Budget vs actual reconciled
All cash deposited and reconciled
Crew paid; receipts filed
Merch inventory counted; reorder
Thank-you notes to promoters and venues
Notes for next time
Progress
Template by TRMNGR · trmngr.com · powered by Inkable Clothing